## Sheet1
Requirement	Description	Location	Status	Description
1	receive data from HDI	SDI_cmd	COMPLETE
1a1	Wheel position	SDI_cmd	COMPLETE
1a2	gas position	SDI_cmd	COMPLETE
1a3	brake position	SDI_cmd	COMPLETE
1a4	gear	SDI_cmd	COMPLETE
1a5	vibration	SDI_cmd	COMPLETE
2	log data from HDI	SDI_cmd	PARTIAL	SDI_listener-1-stdout.log not desired name
2a1	Wheel position	SDI_cmd	COMPLETE
2a2	gas position	SDI_cmd	COMPLETE
2a3	brake position	SDI_cmd	COMPLETE
2a4	gear	SDI_cmd	PARTIAL	value shows errors in log
2a5	vibration	SDI_cmd	COMPLETE
3	SDI send data to HDI	SDI_state	PARTIAL	SDI_talker-2-stdout.log not desired name
3a1	Wheel position	SDI_state	PARTIAL	not well formatted, value doesn't show up
3a2	wheel force	SDI_state	NOT STARTED
3a3	vibration	SDI_state	NOT STARTED
4	log data to HDI	SDI_state	PARTIAL
4a1	Wheel position	SDI_state	COMPLETE
4a2	wheel force	SDI_state	COMPLETE
4a3	vibration	SDI_state	COMPLETE
5	update state of vehicle	SDI_cmd	COMPLETE
5a1	hand wheel position	SDI_cmd	COMPLETE
5a2	gas pedal position	SDI_cmd	COMPLETE
5a3	brake pedal position	SDI_cmd	COMPLETE
5a4	vehicle direction	SDI_cmd	COMPLETE
5a5	hand brake position	SDI_cmd	COMPLETE
5a6	key state	SDI_cmd	COMPLETE	only sent when changed from 1
6	log sim update cmds	SDI_cmd	PARTIAL
6a1	hand wheel position	SDI_cmd	COMPLETE
6a2	gas pedal position	SDI_cmd	COMPLETE
6a3	brake pedal position	SDI_cmd	COMPLETE
6a4	vehicle direction	SDI_cmd	PARTIAL	not well formatted, value doesn't show up
6a5	hand brake position	SDI_cmd	COMPLETE
6a6	key state	SDI_cmd	PARTIAL	not well formatted, value doesn't show up
7	get vehicle state	SDI_state	PARTIAL
7a1	hand wheel position	SDI_state	COMPLETE	set up subscriber
7a2	hand wheel force	SDI_state	NOT STARTED
7a3	vibration	SDI_state	PARTIAL	retrieves key state and uses that to determine key value
7a4	vehicle speed	SDI_state	NOT STARTED
8	log vehicle state	SDI_state	PARTIAL
8a1	hand wheel position	SDI_state	COMPLETE
8a2	hand wheel force	SDI_state	PARTIAL	logging implemented, but not tested
8a3	vibration	SDI_state	PARTIAL	determined by key value, both key and vibration logged, not well formatted, value doesn't show up
8a4	vehicle speed	SDI_state	NOT STARTED

9	environment can be specified by sdf
9a	1+ terrain element location, orientation
9b	location, orientation, mass of all obstacles
9c	material must have frictional value
10	vehicle can be specified by sdf
10a	1+ wheel with material
10b	Mass = sum of components

11	generate environment w/o user config
12	allow user config
12a	path length
12b	terrain composition
12c	Continuous / non-continuous
13	output sdf conforms to requirement 9